## PROJECT
PROJECT_TITLE | PROJECT_ID | PROJECT_DESCRIPTION | TOTAL_REQUIRED_RESOURCE | TOTAL_AVAILABLE_RESOURCE | RESOURCE_TYPE | DONOR_NAME | DONOR_CODE | AMOUNT | COMMENT | CLEARANCE_ROLE | NAME | APPROVAL_DATE | BOARD_DATE
Engagement facility West and Central Africa and the Caribbean | 00092084 / 00117764 / 00126438 |  | 442 398.5 | 442 398.5 | CORE |  |  | 0 | Expected contribution of 86240 USD early 2025 for 11126438 and 100 000 USD on 00117764 | Project Manager | David Larue
[5 empty] | DONOR | UNFPA | 12445 | 111240 |  | Director/Deputy Director for the Practice area | Henri Dommel
[5 empty] | DONOR | LUXEMBOURG | 000155 | 305696.5
[5 empty] | DONOR | UNDP | 12 | 25462
[5 empty] | IN KIND |  |  | 0
Host Government or stakeholder

## OUTPUT 1
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 1 : UNFPA UN2UN agreement in Burkina Faso | Output 1: A campaign on the themes of financial education and SSR (Sexual and Reproductive Health and Rights) is organized for the benefit of 10,000 youth and adolescents.
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
Activity 1.1. Conduct a training campaign on the themes of financial education, entrepreneurship, and SSR for the benefit of young people and adolescents. | Burkina Faso |  | 5000 |  | 6557 | UNCDF | UNFPA | 12445 | 71200/71300 - consultant fees | 11557 | 11557 | 0 | 8

## OUTPUT 2
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 1 : UNFPA UN2UN agreement in Burkina Faso | Output 2: The structuring of youth and adolescents to lead 50 savings clubs is facilitated.
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
Activity 2.1 Support for the structuring of youth and adolescents into savings clubs to mobilize savings - Organization of a youth and adolescent awareness day on financial inclusion | Burkina Faso |  | 4000 |  |  | UNCDF | UNFPA | 12445 | 72100- Contractual Services | 4000 | 4000 | 0 | 8
Activty 2.2:Organizing a awarness day on financial inclusion for youth | Burkina Faso |  | 5000 |  |  | UNCDF | UNFPA | 12445 | 72510- Publications | 5000 | 5000 | 0 | 8

## OUTPUT 3
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 1 : UNFPA UN2UN agreement in Burkina Faso | Output 3: Support is provided to MFIs for the development of innovative and adapted financial services for the benefit of 1,000 youth and adolescents.
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
Actvitiy 3.1.Facilitate the development of financial services for the financing of IGAs or equipment. | Burkina Faso |  | 14662 |  | 14662 | UNCDF | UNFPA | 12445 | 72100- Contractual Services | 29324 | 29324 | 0 | 8
Activity 3.2 Open accounts with financial service providers | Burkina Faso | 2000 | 2176 |  |  | UNCDF | UNFPA | 12445 | 72100- Contractual Services | 4176 | 4176 | 0 | 8

## OUTPUT 4
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 1 : UNFPA UN2UN agreement in Burkina Faso | Output 4:Strengthen the capacities of 100 youth and adolescents on the themes of simplified entrepreneurship (entrepreneurial spirit and management)
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
Actvitiy 4.1. Coaching of young people for the development of innovative projects & mentoring | BURKINA Faso | 1000 | 2176 | 1000 |  | UNCDF | UNFPA | 12445 | 72100- Contractual Services | 4176 | 4176 | 0 | 8
Activity 4.2 Connect with MFIs | BURKINA Faso |  |  | 3342 |  | UNCDF | UNFPA | 12445 | 72100- Contractual Services | 3342 | 3342 | 0 | 8

## OUTPUT 5
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 1 : UNFPA UN2UN agreement in Burkina Faso | Output 6:Coordination-Supervision-Reporting
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
Actvitiy 6.1 One monitoring visit and one capitalization visit | BURKINA Faso |  | 3000 |  | 4250 | UNCDF | UNFPA | 12445 |  | 7250 | 7250 | 0 | 8
Actvitiy 6.2 : Quaterly and final reporting | BURKINA Faso |  |  |  |  | UNCDF | UNFPA | 12445 |  |  |  | 0 | 8
Actvitiy 6.3 : Coordination gestion | BURKINA Faso | 0 | 0 | 0 | 0 |  | UNFPA | 12445 |  | 34175 | 34175 | 0 | 8

## OUTPUT 6
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 2:Evaluation report for the youth portfolio approved and fundraising support to the region | Output 1 : Evaluation report for the youth portfolio approved and fundraising support to the region
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
2.1 Activity Final evaluation of the Youth portfolio | Multi country |  |  | 153052 |  | UNCDF | Luxembourg | 155 | 72100- Contractual Services | 153052 | 153052 | 0
2.2 Regional office costs | Multi country |  |  | 50000 |  | UNCDF | Luxembourg | 155 | 72100- Contractual Services | 50000 | 50000
2.3 Activity Contributing to development of opportunities in the region (concept notes, proposals, etc) | Multi country |  |  | 80000 |  | UNCDF | Luxembourg | 155 | 71400 - IPSA salary, 61300 - Staff salary, 71600 - Travel | 80000 | 80000

## OUTPUT 7
PROJECT_OUTCOME | PROJECT_OUTPUT
Outcome 3:Positioning and fundraising effort in Madagascar supported | Output 1 :Positioning and fundraising effort in Madagascar supported
PLANNED_ACTIVITY | COUNTRY | Q1 | Q2 | Q3 | Q4 | RESPONSIBLE_PARTY | DONOR | DONOR_CODE | BUDGET_DESCRIPTION | ANNUAL_BUDGET | AMOUNT_FUNDED | AMOUNT_UNFUNDED | GMS | Q1_EXPENDITURE | Q2_EXPENDITURE | Q3_EXPENDITURE | Q4_EXPENDITURE | PROGRESS
3.1 Activity Contributing to the INFF exercise in Madagascar Developing a country Prodoc that will host upcoming opportunities. | Madagascar |  | 23576 |  |  | UNCDF | UNDP | 12 | 71200/71300 - consultant fees , 71600 - Travel | 23576 | 23576 |  | 8

## INDICATOR 1
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE
UNCDF SF OP 4.2:The Number of people who have received capacity development support | Total | 0 | 2025 | 7000
UNCDF SF OP 4.2:The Number of people who have received capacity development support | Youth | 0 | 2025 | 7000
UNCDF SF OP 4.2:The Number of people who have received capacity development support | Women | 0 | 2025 | 3500

## INDICATOR 2
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE
UNCDF SF OC 1.4 : The number of people engaging with UNCDF-supported products, services and infrastructures | Total | 0 | 2025 | 50
UNCDF SF OC 1.4 : The number of people engaging with UNCDF-supported products, services and infrastructures | engaging with | 0 | 2025 | 50
UNCDF SF OC 1.4 : The number of people engaging with UNCDF-supported products, services and infrastructures | youth | 0 | 2025 | 50
UNCDF SF OC 1.4 : The number of people engaging with UNCDF-supported products, services and infrastructures | women |  | 2025 | 25
Project Indicator 2.1 : Number of clubs created |  | 0 | 2025 | 50
Project Indicator 2.2 : Total amount of savings mobilized |  | 0 | 2025 | 20000000 | XOF

## INDICATOR 3
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE
Project Indicator 3.1 : Number of accounts opened by young people | Total | 0 | 2025 | 189
Project Indicator 3.1 : Number of accounts opened by young people | Women | 0 | 2025 | 92
Project Indicator 3.2 : :Number of young people receiving start-up kits | Total | 0 | 2025 | 150
Project Indicator 3.2 : :Number of young people receiving start-up kits | Women | 0 | 2025 | 75

## INDICATOR 4
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE
UNCDF SF OP 4.2:The number of people who have received capacity development support | Total | 0 | 2025 | 100
UNCDF SF OP 4.2:The number of people who have received capacity development support | Youth | 0 | 2025 | 100
UNCDF SF OP 4.2:The number of people who have received capacity development support | Women | 0 | 2025 | 50
Project Indicator 4.1 : Number of young people trained and coached in simplified entrepreneurship | Total | 0 | 2025 | 100
Project Indicator 4.1 : Number of young people trained and coached in simplified entrepreneurship | Women | 0 | 2025 | 50

## INDICATOR 5
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE

## INDICATOR 6
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE
Evaluation report for the youth portfolio approved |  | 0 | 2025 | 1

## INDICATOR 7
INDICATOR | DISAGGREGATION | BASELINES | YEAR | ANNUAL_TARGET | UNIT | MID_YEAR_ACTUALS | END_YEAR_ACTUALS | DATA_SOURCE
1 INFF done with UNDP |  | 0 | 2025 | 1
1 Country PRODOC validated |  | 0 | 2025 | 1
3 Concept Note presented to donors |  | 0 | 2025 | 3